## Intstructions
Instructions
1. Open safearth.in on a computer to do the testing
2. Follow the instructions for each test case in the second sheet
3. For all cases test cases that pass, highlight in green
4. For all test cases that fail, highlight in red
5. For all failed test cases, write the reason of failure in the actual results coloumn

## Vendor Side Website
Product Name |  | Marketplace
Module Name |  | Vendor Side Website
Created By |  | SafEarth
Website Link |  | https://safearth.in/
Content Page Link |  | <To be Added>
Test Scenario ID | Main Page | Sub Pages | Test Scenario Description | Test Case Description | Test Step | Expected result | Actual result | Status | Executed date | Executed By | Comments (if any)
LP1 | Landing page | Landing Page | Access to the Solar Installers Landing page | Grow my business should lead to Vendor Landing page | 1) Click on the Grow My Business Button. 2) Redirected page link https://safearth.in/landing/vendor | page opens: https://safearth.in/landing/vendor | https://safearth.in/landing/vendor | pass | yes | Damini
LP2 |  | Landing Page | Access to the Customers Landing page | Switch to Clean Energy Button should lead to Customer Landing page | 1) Click on the Switch to Clean Energy Button. 2) Redirected page link https://safearth.in/landing/customer | page opens: https://safearth.in/landing/customer | https://safearth.in/landing/customer | pass | yes | Damini
LP3 |  | Landing Page -> Log In | Log in to marketplace from Landing Page | Flow to test the logging in to Marketplace from Landing page | 1) Click Log In 2) Click on Marketplace | Page Opens: https://safearth.in/logIn/customer |  | fail | yes | Damini | when clicking on Log In to marketplace from landing page it showing one dialog box with two optoins one is as a coustomer and one is asa vendor.
LP4 |  | Landing Page -> Log In | Log In Solar Flow from Landing Page | Flow to test the logging in to Solar Flow from Landing page | 1) Click Log In 2) Click on Solar Flow | Page Opens: https://pmt.safearth.in/login |  | Fail | yes | Damini | when clicking on log In there no option for solar flow
LP5 |  | Landing Page -> Sign Up | Access to Customer Sign Up | Flow to test the signing up as customers from the Landing page | 1) Click on Sign Up 2) Click on As a Customer Button | Page Opens https://safearth.in/signUp/customer | https://safearth.in/signUp/customer | pass | yes | Damini
LP6 |  | Landing Page -> Sign Up | Access to Vendor Sign Up | Flow to test the signing up as vendors from the Landing page | 1) Click on Sign Up 2) Click on As a Vendor Button | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP7 | Vendors Landing page: https://safearth.in/landing/vendor | Nav bar | Products Tab | Product Tab should open a drop down for selecting the product that the user wants to find out about | 1) Click on the Products Tab | Drop Down opens with 2 buttons: Project marketplace, Solar Flow |  | pass | yes | Damini
LP8 |  | Nav bar | Product Tab: Project Marketplace | Checking the Project marketplace Button on the Nav Bar | 1) Click on the Products Tab 2) Click on the Projects Marketplace Button | Page Opens: https://safearth.in/projects | https://safearth.in/projects | pass | yes | Damini
LP9 |  | Nav bar | Product Tab: Solar Flow | Checking the Solar Flow Button on the Nav Bar | 1) Click on the Products Tab 2) Click on the Solar Flow Button | Page Opens: https://pmt.safearth.in/ | https://pmt.safearth.in/ | pass | yes | Damini
LP10 |  | Nav bar | Foundation Tab on Nav bar | Checking the Foundation Tab on the Nav Bar | 1) Click on the Foundation Tab | Page Opens: https://safearthfoundation.org/ in new tab | https://safearthfoundation.org/ | pass | yes | Damini | when click on foundation tab new page open on new tab
LP11 |  | Nav bar | Blog Tab on Nav bar | Checking the Blog Tab on the Nav Bar | 1) Click on the Blog Tab | Page Opens: https://blog.safearth.in/ in new tab | https://blog.safearth.in/ | pass | yes | Damini | when click on blog tab new page open on new tab
LP12 |  | Nav bar | Team Tab on Nav bar | Checking the Team Tab on the Nav Bar | 1) Click on the Team Tab | Page Opens: https://safearth.in/team | https://safearth.in/team | pass | yes | Damini | when click on team tab on same tab list of team members displayed and calculator tab added on Nav bar
LP13 |  | Nav bar | Contact Us Tab on Nav bar | Checking the Contact Us Tab on the Nav Bar | 1) Click on the Contact Us Tab | Page Opens: https://safearth.in/contactUs | https://safearth.in/contactUs | pass | yes | Damini | new page opened on same tab
LP14 |  | Nav bar | Log In to marketplace from the Nav bar | Checking the Marketplace Log In from the Nav Bar | 1) Click on Log In 2) Click on the Marketplace button | Page Opens: https://safearth.in/logIn/customer | https://safearth.in/logIn/vendor | fail | yes | Damini | login from vendor page did not open customer page. url was seen as vendor
LP15 |  | Nav bar | Log In to Solar Flow from the Nav bar | Checking the Solar Flow Log In from the Nav Bar | 1) Click on Log In 2) Click on the Solar Flow button | Page Opens: https://pmt.safearth.in/login |  | fail | yes | Damini | solar flow log In is not seen on Nav bar
LP16 |  | Nav bar | Nav Bar Consistency Between Different Pages | nav bar should be consistent through all the pages of the vendor side | 1) Navigate through each of the sections of the landing page for vendors. 2) Observe the Nav bar in each of the page where the page is not opening ina new tab | Whenever the page is opening in the same tab, the nav bar should be consistent and the user should have the same navigation options in the nav bar. |  | fail | yes | Damini | when page opening in the same tab Nav bar is not consistant . when user clicks on team tab on nav nar , calculator tab is added on nav bar.
LP17 |  | Nav bar | Sign Up from the nav bar | Checking the Sign Up from the Nav bar | 1) Click on the Sign Up Button on Nav bar | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP18 |  | Vendor landing page | Find Out How | Action Post Find Out how | 1) Click on Find Out How on the Landing page | Scrolls to the below section |  | pass | yes | Damini
LP19 |  | Vendor landing page | Link to Gallery | Action post link to Gallery Clicking | 1) Click on the Link to gallery below the carasoule | Page Opens: https://safearth.in/projects | https://safearth.in/projects | pass | yes | Damini
LP20 |  | Vendor landing page | Gallery Arrows | Action Post gallery Arrows in the Landing page | 1) Click on the right Arrow multiple times 2) Click on the left Arrow multiple times | Different projects are shown in the carousel |  | pass | yes | Damini
LP21 |  | Vendor landing page | Pre Sales - Post Sales Switch | Once the user has come to the How does it work section, he should be able to move between different stages easily | 1) Click on Post Sales 2) Click on Pre Sales | 1) Upon Clicking Post Sales, User can see the details of Project Planning and Tracking in the RHS side of the Table 2) Upon clicking Pre Sales, user should be able to see the equirement Assessment details in the RHS Sdie of the table |  | pass | yes | Damini
LP22 |  | Vendor landing page | Requirement Assessment, Online Bidding, Project Closure, Project Planning and Tracking and Tracking, Quality Control, O&M switch | Switch between different steps of the process | 1) Click each of the 6 steps one by one | 1) User should see the details of that particular step in the RHS and the stage of that particular stage should be highlighted in the LHS |  | pass | yes | Damini
LP23 |  | Vendor landing page | Scrolling through the page | Scrolling through the website should be smooth and in one go | 1) Scroll through different sections, from top to bottom and bottom to top | 1) User should be able to flick through the website, one small flick takes them to the next section. 2) Down flick takes the user down and up flick takes the user up 3) No UI issues in the flicking |  | pass | yes | Damini
LP24 |  | Vendor landing page | Sell Solar Plants GIF | Sell Solar Plant image on the LHS is a GIF. It should be working properly | 1) Come to the Sell Solar plant section below How it works. 2) Observe the GIF for 10 seconds | The GIF should be flowing in auto repeat mode constantly |  | fail | yes | Damini | GIF is not flowing in auto repeat mode costantlyy its stop after one iteration
LP25 |  | Vendor landing page | View Our Projects Button on the Sell Solar Plants Section | View Our project Button takes the user to the Projects page | 1) Come to the Sell Solar Plant Section 2) Click on the View Our projects Button | Page Opens: https://safearth.in/projects | https://safearth.in/projects | pass | yes | Damini
LP26 |  | Vendor landing page | Automate your Solar Plants Installation GIF | Automate your Solar Plant image on the RHS is a GIF. It should be working properly | 1) Come to the Automate your Solar plant Installation section below Sell Solar Plants 2) Observe the GIF for 10 seconds | The GIF should be flowing in auto repeat mode constantly |  | fail | yes | Damini | GIF is not flowing in auto repeat mode costantlyy its stop after one iteration
LP27 |  | Vendor landing page | Find Out How Button on the Automate Your Solar Plants Installation Section | Find Out how Button takes the user the the Landing page for Solar Flow | 1) Come to the Automate your Solar Plant Installation Section below the Sell Solar Plant Section 2) Click on the Find Out How Button below the 4 features | Page Opens: https://pmt.safearth.in/ |  | fail | yes | Damini | find out how' botton is not present in
LP28 |  | Vendor landing page | Switching Different Features in the Automate your solar Plant Installation Section | User should be easily able to switch between different features in this section | 1) Come to the Automate your Solar Plant Installation Section below the Sell Solar Plant Section 2) Wait for 5 seconds to see if the new feature opens up in detail once the progress bar runs Out 3) Click on the different features and see if they open up | 1) Once the Progress bar is completed, the new feature should open up automaitcally and the current feature should close 2) Upon clicking any of the features, they should open up completely and the currently opened feature should close |  | pass | yes | Damini
LP29 |  | Vendor landing page | Important Figures GIF | Important Figures GIF on the RHS is a GIF. It should be working properly | 1) Come to the Important Figures Section below the Automate your solar plant installation section 2) Observe the GIF for 10 seconds | The GIF should be flowing in auto repeat mode constantly |  | fail | yes | Damini | GIF is not flowing in auto repeat mode costantlyy its stop after one iteration
LP30 |  | Vendor landing page | Become a Vendor Button | Become a Vendor Button is a button to redirect to the Sign Up page of vendors | 1) Come to the Important Figures Section below the Automate your solar plant installation section 2) Click on the BEcome a Vendor Button | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP31 |  | Vendor landing page | SafEarth in the News Section | These are all the press that SafEarth has received | 1) Come to the Our Clients / News Section below the Important Figures section 2) Click on the Each of the links in the media section | Each of the press items should be a valid link that redirects to the respective media website in a new tab |  | pass | yes | Damini
LP32 |  | Vendor landing page | Our Clients Carousle | Multiple clients shown in the caraousle, it should be working properly | 1) Come to the Our Clients / News Section below the Important Figures section 2) Observe the client caraousel for 10 seconds 3) Click on the dot below this section | 1) The client carousel should be auto moving. 2) Clicking on the dots below should take to the next section |  | pass | yes | Damini
LP33 |  | Content Check | Detailed Checking of the content of each section of the page | Run through the content and compare it with the content page of the website shared on Drive | 1) Read the content of each section of the page and verify it against the content page above | 1) Content should be the same 2) All content should be in the correct format |  |  | No |  | content page link is not given
LP34 |  | Vendor Footer | Our projects in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth.in/projects | https://safearth.in/projects | pass | yes | Damini
LP35 |  | Vendor Footer | Our Vendors in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens https://safearth.in/becomeAVendor | https://safearth.in/projects | fail | yes | Damini | clicking on our vendor projects page displayed.
LP36 |  | Vendor Footer | Contact Us in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth.in/contactUs | https://safearth.in/contactUs | pass | yes | Damini
LP37 |  | Vendor Footer | Testimonial in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: Page needs to be Designedned | https://safearth.in/projects | fail | yes | Damini | prjects page is seen. insted of under construction page.
LP38 |  | Vendor Footer | Become a Vendor in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens https://safearth.in/becomeAVendor | https://safearth.in/becomeAVendor | pass | yes | Damini
LP39 |  | Vendor Footer | Project Marketplace in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Takes the User up to the Sell Solar Plants Section |  | fail | yes | Damini
LP40 |  | Vendor Footer | Component Marketplace in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Should not be there |  | fail | yes | Damini | though component marketplace should not be there in the vendor footer but it is present
LP41 |  | Vendor Footer | Log in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth.in/logIn/customer | https://safearth.in/logIn/vendor | fail | yes | Damini
LP42 |  | Vendor Footer | Sign Up in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP43 |  | Vendor Footer | FAQ in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth.in/faq | https://safearth.in/faq | pass | yes | Damini
LP44 |  | Vendor Footer | Solar in different regions in the geography in vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth.in/projects | https://safearth.in/projects | pass | yes | Damini
LP45 |  | Vendor Footer | Privacy Policy in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: \ | https://safearth-pmt-static.s3.ap-south-1.amazonaws.com/Final+Data+Policy.pdf | pass | yes | Damini
LP46 |  | Vendor Footer | Sitemap in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Site Map Page Opens | https://safearth.in/sitemap.xml | fail | yes | Damini | UI did not load not sitemap page.
LP47 |  | Vendor Footer | Terms of Use in Vendor Footer | This is a link and should open the right page | 1) Arrive at the Footer in the landing page 2) Click the Respective Link | Page Opens: https://safearth-pmt-static.s3.ap-south-1.amazonaws.com/20220920+ToS.pdf | https://safearth.in/terms-and-conditions | fail | yes | Damini | new page of terms and conditions opened on the same tab
LP48 |  | Floating Action Button | Floating Action Button is there to make the platform easily navigable | Flaoting action Button should be there throughout the landing page | 1) Scroll down through the whole landing page and see if the floating button is there in the bottom right of each section. 2) Scroll up through the whole landing page and see if the floating button is there in the bottom right of each section. | 1) Floating button should be there in all sections, including the footer |  | fail | yes | Damini | floating botton is not available in sections - our clients,safearth in the news and footer.
LP49 |  | Floating Action Button | Opening the FLoating Button | The Floating Menu opens Up | 1) Click on the Flating Action Button on the Bottom right of the screen | 1) The Button should Open the Floating Menu |  | pass | yes | Damini
LP50 |  | Floating Action Button | Become a vendor in the Flaoting Action Button | Easy navigation mode for become a vendor at Any Time | 1) Click on the Flating Action Button on the Bottom right of the screen 2) Click on Become a Vendor Button | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP51 |  | Floating Action Button | Book a Site Visit in the Floating Action Button | Easy navigation mode for Book a Site Visit at Any Time | 1) Click on the Flating Action Button on the Bottom right of the screen 2) Click on book a Site Visit Button | Page Opens: https://safearth.in/logIn/customer |  | fail | yes | Damini | new popup opened after clicking on book a site visit
LP52 |  | Floating Action Button | Contact Us in the Floating Action Button | Easy navigation mode for Contact Us at Any Time | 1) Click on the Flating Action Button on the Bottom right of the screen 2) Click on Contact Us Button | Page Opens: https://safearth.in/contactUs |  | fail | yes | Damini | new popup opened after clicking on contactUs
LP53 | Projects Page Vendors: https://safearth.in/projects | 1st Section | Join Now Button | Join Now Should take to Sign Up | 1) From Vendor Landing page, open the Marketplace page 2) Click on Join Now | Page Opens https://safearth.in/signUp/vendor | https://safearth.in/signUp/vendor | pass | yes | Damini
LP54 |  | 2nd Section | Take me to the Future of Solar | Take me to the Future of Solar to take to Log In | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the 2nd section of this page 3) Click on Take me to the Future of Solar button | Page Opens: https://safearth.in/logIn/customer | https://safearth.in/logIn/vendor | fail | yes | Damini | vendor log In page opened
LP55 |  | 3rd Section | Our Projects Section UI Check | Check UI | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the 3rd section of this page 3) Check if the UI is perfect or not | Projects should be clearly visible, section should cover the whole of the page |  | pass | yes | Damini
LP56 |  | 3rd Section | Our Projects Section Data Validation | Data | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the 3rd section of this page 3) Check if all the projects are visible here or not | As on 23rd November, it should be close to 50+ projects |  | fail | yes | Damini | only 31 projects are visible
LP57 |  | 3rd Section | View project Details Buttons Validation | View project should show the details of the project | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the 3rd section of this page 3) Click on View project Details of atleast 10 projects | Pop Should open for each of the project showing its complete details |  | pass | yes | Damini
LP58 |  | Content Check | Detailed Checking of the content of each section of the page | Run through the content and compare it with the content page of the website shared on Drive | 1) Read the content of eeach section of the page and verify it against the content page above | 1) Content should be the same 2) All content should be in the correct format |  |  | No | Damini | content page link is not given
LP59 |  | Scrolling through the page | Scrolling through the project page | Scrolling through the website should be smooth and in one go (flick Scroll) | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the bottom of the page 3) Navigate back to the top of the page | 1) User should be able to flick through the website, one small flick takes them to the next section. 2) Down flick takes the user down and up flick takes the user up 3) No UI issues in the flicking |  | pass | yes | Damini | scrolling is smooth and one flick go to the next section
LP60 |  | Footer Check | Check if the footer check of the nav bar is valid or not | Should be the same footer | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the footer of the page 3) Check each link of the footer similar to the landing page check | Footer test should produce the same results as the landing page |  | pass | yes | Damini
LP61 | Team Page: https://safearth.in/team | Scrolling through the page | Scrolling through the project page | Scrolling through the website should be smooth and in one go (flick Scroll) | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the bottom of the page 3) Navigate back to the top of the page | 1) User should be able to flick through the website, one small flick takes them to the next section. 2) Down flick takes the user down and up flick takes the user up 3) No UI issues in the flicking |  | pass | yes | Damini | scrolling is smooth and one flick go to the next section
LP62 |  | Content Check | Detailed Checking of the content of each section of the page | Run through the content and compare it with the content page of the website shared on Drive | 1) Read the content of each section of the page and verify it against the content page above | 1) Content should be the same 2) All content should be in the correct format |  |  | No | Damini | content page link is not given
LP63 |  | First Page | Down Button Check | Clicking on the down button should navigate below | 1) Open the Teams Page 2) Click on the Down Button | You should be navigated to the section below |  | pass | yes | Damini | Below section navigated
LP64 |  | Teams Section | Emails Check | Emails of respective team members should open | 1) Open the Teams Page 2) Come to the teams section 3) Check the emails icon of all the team members | All emails should open up the emails of the respective team member |  | pass | yes | Damini
LP65 |  | Teams Section | LinkedIn Check | LinkedIn of respective team members should open | 1) Open the Teams Page 2) Come to the teams section 3) Check the LinkedIn icon of all the team members | All LinkedIn icons should open up the LinkedIn of the respective team member |  | pass | yes | Damini
LP66 |  | Teams Section | Join the Team Button | Scroll to the section below | 1) Open the Teams Page 2) Come to the teams section 3) Click on the Join the Team Button | User should be scrolled to the open roles section |  | fail | yes | Damini | join the team botton is not clickable
LP67 |  | New Roles Section | Jobs Section Check | Navigation between different sections | 1) Open the Teams Page 2) Come to the Jobs section 3) Click on all the mentioned departments | User should be navigated between the different sections |  | pass | yes | Damini
LP68 |  | New Roles Section | Apply Now Button | Apply now button opens the application dialogue Box | 1) Open the Teams Page 2) Come to the Jobs section 3) Click on apply now to some open role | Pop Up for application should be opened up |  |  | NO | Damini | no jobs were available at the time of testing
LP69 |  | New Roles Section | Application process | Application for a Particular Role | 1) Open the Teams Page 2) Come to the Jobs section 3) Click on apply now to some open role 4) Fill the fomr and enter submit | Job application should be submitted and you should get an email in the concerned email ID for that role |  |  | NO | Damini | no jobs were available at the time of testing
LP70 |  | New Roles Section | Search Check | Job posts have been designed to be searchable | 1) Open the Teams Page 2) Come to the Jobs section 3) Use the search window to search different terms | The internal window should reflect the required changes |  |  | NO | Damini | search bo is available but no jobs availble in the section could not exicute this test case.
LP71 |  | Footer Check | Check if the footer check of the nav bar is valid or not | Should be the same footer | 1) From Vendor Landing page, open the Marketplace page 2) Navigate to the footer of the page 3) Check each link of the footer similar to the landing page check | Footer test should produce the same results as the landing page |  | pass | yes | Damini | footer is same as landing page
LP72 | Contact Us Page : https://safearth.in/contactUs | Content Check | Detailed Checking of the content of each section of the page | Run through the content and compare it with the content page of the website shared on Drive | 1) Read the content of each section of the page and verify it against the content page above | 1) Content should be the same 2) All content should be in the correct format |  |  | No | Damini | content page link is not given
LP73 |  | States with project | States with project | Should be coming in from the active states in the project section | 1) Compare the active states in the Contact us Section and see the states in the Project Section of the Prject page | 1) Only states which are mentioned in the project sections should be shown as active states here |  | pass | yes | Damini | states which are mentioned in the project sections are shown as active states in contactUs.
LP74 |  | Office Address | Office Address | Check the Office Address of both the office | 1) Hover over the Office address of all the offices | Correct office address should be visible for Delhi, bangalore, jaipur, Ranchi and Hyderabad |  | fail | yes | Damini | Correct office address visible for Delhi, bangalore, and for jaipur, Ranchi Hyderabad address is not visible.
LP75 |  | Contact Us Form | Contact Us Form | Fill out the form | 1) Fill out the Complete Form | Success Message should come |  | pass | yes | Damini
LP76 |  | Contact Us Form | Contact Us Form | Validity Check | Fill out the partial form | It should show an error message: All Fields are mandatory |  | fail | yes | Damini | comment field is not mandatory. we were able to submit the form with wrong email address,
LP77 |  | We Are hiring | We Are hiring | Quick Link to see the roles that are available | 1) Click on We are Hiring | User is Redirected to the open roles in the teams page |  | fail | yes | Damini | User is not Redirected to the open roles in the teams page, it gives pop Up .
LP78
LP79
LP80
LP81
LP82
LP83
LP84
LP85
LP86
LP87
LP88
LP89
LP90
LP91
LP92
LP93
LP94
LP95
LP96
LP97
LP98
LP99
LP100
LP101
LP102
LP103
LP104
LP105
LP106
LP107
LP108
LP109
LP110
LP111
LP112
LP113
LP114
LP115
LP116
LP117
LP118
LP119
LP120
LP121